## StayliaApp_Estimates
Sr. No. | Module Name |  | Module Description | Est Time (Hrs.) | Total Hours for Backend (Hrs.) | Total Hours for React-Native App (Hrs.)
1 | Database Structure | 1 | DB Structure for the complete Mobile App | 3 | 3
2 | Setup and Installation | 1 | Project Setup with Node and TypeScript | 3 | 17
|  | 2 | MongoDB integration with mongoose | 1
|  | 3 | Twilio Integration | 1
|  | 4 | SMTP Email Integration | 1
|  | 5 | Firebase Notification Integration | 1
|  | 6 | ElasticSearch Integration | 10
3 | Authenticaion APIs | 1 | Login with Mobile OTP | 2 | 11 | 16
|  | 2 | Signup with Mobile Number | 2
|  | 3 | Verify OTP | 1
|  | 4 | Resent OTP | 1
|  | 5 | Login with Password for Agent and Admin | 1
|  | 6 | Social Sign in | 2
|  | 7 | Forget Password | 2
4 | User Profile APIs | 1 | View Profile | 1 | 11 | 16
|  | 2 | Update Profile | 1
|  | 3 | List of Saved Properties | 3
|  | 4 | List of Saved Agents | 3
|  | 5 | Save/Unsave Property | 1
|  | 6 | Save/Unsave Agent | 1
|  | 7 | Notification Settings | 1
5 | Property APIs | 1 | Featured + Newly Added Properties | 4 | 38 | 32
|  | 2 | Nearby Properties | 4
|  | 3 | List of Properties (Buy & Rent) | 6
|  | 4 | Property Details + Amenities | 4
|  | 5 | Property Search + Advance Search | 8
|  | 6 | Filter Properties | 5
|  | 7 | Add Property | 4
|  | 8 | Edit/Update Property | 2
|  | 9 | Delete Property | 1
6 | Agent APIs | 1 | List of Agents | 4 | 17 | 20
|  | 2 | Search Agent + Advance Search | 6
|  | 3 | List of Properties against Agent ID | 2
|  | 4 | Agent Details | 2
|  | 5 | Nearby Agents | 3
7 | Notifications APIs | 1 | Get All Notifications | 1 | 18 | 8
|  | 2 | Get Notification Details | 1
|  | 3 | Send Notifications | 2
|  | 4 | Send Push Notifications | 2
|  | 5 | Send Email Notifications | 4
|  | 6 | Send Text Message Notifications | 4
|  | 7 | Reminder Email Notification | 4
8 | Chat APIs | 1 | List of Conversations | 2 | 8 | 22
|  | 2 | Conversation Details (List of Messages) | 2
|  | 3 | Send/Receive Messages | 1
|  | 4 | Message Notification | 2
|  | 5 | Message Counter | 1
9 | FAQs APIs | 1 | View All FAQs | 1 | 4 | 8
|  | 2 | FAQ Details | 0
|  | 3 | Add FAQs | 1
|  | 4 | Update/Edit FAQs | 1
|  | 5 | Delete FAQs | 1
10 | Support | 1 | 3rd Party SDK Provided by client | 3 | 3 | 8
11 | Agent APIs | 1 | Add Agent | 2 | 6
|  | 2 | Edit/Update Agent | 2
|  | 3 | View Agent Details | 1
|  | 4 | Delete Agent | 1
12 | Agency APIs | 1 | Add Agency | 2 | 5
|  | 2 | Edit/Update Agency | 1
|  | 3 | View Agency Details | 1
|  | 4 | Delete Agency | 1
13 | Users APIs | 1 | Add User | 1 | 4
|  | 2 | Edit/Update User | 1
|  | 3 | View User Details | 1
|  | 4 | Delete User | 1
14 | Amenities APIs | 1 | Add Amenities | 2 | 6
|  | 2 | Edit/Update Amenities | 2
|  | 3 | View Amenities Details | 1
|  | 4 | Delete Amenities | 1
15 | Specialities APIs | 1 | Add Specialities | 2 | 6
|  | 2 | Edit/Update Specialities | 2
|  | 3 | View Specialities Details | 1
|  | 4 | Delete Specialities | 1
16 | Currencies APIs | 1 | Add Currency | 1 | 4
|  | 2 | Edit/Update Currency | 1
|  | 3 | View Currency Details | 1
|  | 4 | Delete Currency | 1
| Total: |  |  | 161 |  | 130
| Grand Total: |  |  | 291

## Sprint_Planning
Sprint # | Modules Included | Hours of Module | Total Hours of Sprint
Sprint - 1 [Backend APIs Development] | Database Structure | 3 | 40 | Week 1
| Setup and Installation | 17
| Authenticaion APIs | 11
| User Profile APIs | 9
| User Profile APIs | 2 | 40 | Week 2
| Property APIs | 38
Sprint - 2 [Backend APIs Development] | Agent APIs | 17 | 81
| Notifications APIs | 18
| Chat APIs | 8
| FAQs APIs | 4
| Support | 3
| Agent APIs | 6
| Agency APIs | 5
| Users APIs | 4
| Amenities APIs | 6
| Currencies APIs | 4
| Specialities APIs | 6
Sprint - 3 [APIs Integration and Functionality in React-Native App] | Authenticaion APIs | 16 | 64
| User Profile APIs | 16
| Property APIs | 32
Sprint - 4 [APIs Integration and Functionality in React-Native App] | Agent APIs | 20 | 66
| Notifications APIs | 8
| Chat APIs | 22
| FAQs APIs | 8
| Support | 8

## Sheet1
| weekOne |  | weekTwo |  | weekThree |  | wekkFour |  | weekFive |  | weekSix
1 | Signup with Mobile Number | 10 | Save/Unsave Property | 35 |  | 45 | Notification Settings | 25 | List of Properties against Agent ID | 31 | Send Push Notifications
2 | Login with Mobile OTP | 11 | List of Saved Properties | 36 |  | 14 | Featured + Newly Added Properties | 28 | Get All Notifications | 32 | Send Email Notifications
3 | Verify OTP | 12 | Save/Unsave Agent | 37 |  | 16 | List of Properties (Buy & Rent) | 29 | Get Notification Details | 33 | Send Text Message Notifications
4 | Resent OTP | 13 | List of Saved Agents | 38 |  | 17 | Property Details + Amenities | 30 | Send Notifications | 34 | Reminder Email Notification
5 | Login with Password for Agent and Admin | 18 | Add Property | 39 |  | 22 | Property Search + Advance Search
6 | Forget Password | 19 | Edit/Update Property | 40 | View All FAQs | 25 | Search Agent + Advance Search
7 | Social Sign in | 20 | Delete Property | 41 | FAQ Details
8 | View Profile | 21 | Filter Properties | 42 | Add FAQs
9 | Update Profile | 23 | List of Agents | 43 | Update/Edit FAQs
|  | 24 | Nearby Properties | 44 | Delete FAQs
|  | 26 | Agent Details
|  | 27 | Nearby Agents
| completed |  | in working

## updated list 15-02-2022
1 | Signup with Mobile Number | 31 | Send Push Notifications | 65 | add bedRoom type | 95 | add agent
2 | Login with Mobile OTP | 32 | Send Email Notifications | 66 | update bedRoom type | 96 | update agent
3 | Verify OTP | 33 | Send Text Message Notifications | 67 | delete bedRoom type | 97 | delete agent
4 | Resent OTP | 34 | Reminder Email Notification | 68 | view bedRoom type | 98 | view agent
5 | Login with Password for Agent and Admin | 41 | FAQ Details | 69 | all bedRoom types | 99 | all agent
6 | Forget Password | 42 | Add FAQs | 70 | add funished type | 100 | add specialities
7 | Social Sign in | 43 | Update/Edit FAQs | 71 | update funished type | 101 | update specialities
8 | View Profile | 44 | Delete FAQs | 72 | delete funished type | 102 | delete specialities
9 | Update Profile | 45 | addCountry | 73 | view funished type | 103 | view specialities
10 | Save/Unsave Property | 46 | Update/Edit Country | 74 | all funished types | 104 | all specialities
11 | List of Saved Properties | 47 | Delete Country | 75 | add tags | 105 | add terms&conditions
12 | Save/Unsave Agent | 48 | view Country | 76 | update tags | 106 | update terms&conditions
13 | List of Saved Agents | 49 | all Countried | 77 | delete tags | 107 | delete terms&conditions
18 | Add Property | 50 | add Language | 78 | view tags | 108 | view terms&conditions
19 | Edit/Update Property | 51 | delete Language | 79 | all tags | 109 | all terms&conditions
20 | Delete Property | 52 | update Language | 80 | add overView
21 | Filter Properties | 53 | view Language | 81 | update overView
23 | List of Agents | 54 | all Language | 82 | delete overView
24 | Nearby Properties | 55 | add additional info | 83 | view overView
25 | List of Properties against Agent ID | 56 | delete additional info | 84 | all overViews
45 | Notification Settings | 57 | update additional info | 85 | add amenities
14 | Featured + Newly Added Properties | 58 | view single additional info | 86 | update amenities
16 | List of Properties (Buy & Rent) | 59 | all infos | 87 | delete amenities
17 | Property Details + Amenities | 60 | add property type | 88 | view amenities
22 | Property Search + Advance Search | 61 | update property type | 89 | all amenities
26 | Search Agent + Advance Search | 62 | delete property type | 90 | add agency
28 | Get All Notifications | 63 | view property type | 91 | update agency
29 | Get Notification Details | 64 | all property types | 92 | delete agency
30 | Send Notifications |  |  | 93 | view agency
|  |  |  | 94 | all agency

## Updated API with Status 1-3-22
SR# | API Name | Status
1 | Signup with Mobile Number | Done
2 | Login with Mobile OTP | Done
3 | Verify OTP | Done
4 | Resent OTP | Done
5 | Login with Password for Agent and Admin | Done
6 | Forget Password | Done
7 | Social Sign in | Done
8 | View Profile | Done
9 | Update Profile | Done
10 | Save Property | Done
11 | Unsave Property | Done
12 | List of Saved Properties | Done
13 | Save/Unsave Agent | Done
14 | List of Saved Agents | Done
15 | Add Mobile Property | Done
16 | Edit/Update Mobile Property | Done
17 | Delete Mobile Property | Done
18 | Filter Properties | Done
19 | List of Agents | Done
20 | Nearby Properties
21 | List of Properties against Agent ID | Done
22 | Notification Settings | Done
23 | Featured + Newly Added Properties
24 | List of Properties (Buy & Rent) | Done
25 | Property Details + Amenities | Done
26 | Property Search + Advance Search
27 | Search Agent + Advance Search
28 | Get All Notifications
29 | Get Notification Details
30 | Send Notifications
31 | Send Push Notifications
32 | Send Email Notifications
33 | Send Text Message Notifications
34 | Reminder Email Notification
35 | FAQ Details | Done
36 | Add FAQs | Done
37 | Update/Edit FAQs | Done
38 | Delete FAQs | Done
39 | addCountry | Done
40 | Update/Edit Country | Done
41 | Delete Country | Done
42 | view Country | Done
43 | all Countried | Done
44 | add Language | Done
45 | delete Language | Done
46 | update Language | Done
47 | view Language | Done
48 | all Language | Done
49 | add additional info | Done
50 | delete additional info | Done
51 | update additional info | Done
52 | view single additional info | Done
53 | all infos | Done
54 | add property type | Done
55 | update property type | Done
56 | delete property type | Done
57 | view property type | Done
58 | all property types | Done
59 | add bedRoom type | Done
60 | update bedRoom type | Done
61 | delete bedRoom type | Done
62 | view bedRoom type | Done
63 | all bedRoom types | Done
64 | add funished type | Done
65 | update funished type | Done
66 | delete funished type | Done
67 | view funished type | Done
68 | all funished types | Done
69 | add tags | Done
70 | update tags | Done
71 | delete tags | Done
72 | view tags | Done
73 | all tags | Done
74 | add overView | Done
75 | update overView | Done
76 | delete overView | Done
77 | view overView | Done
78 | all overViews | Done
79 | add amenities | Done
80 | update amenities | Done
81 | delete amenities | Done
82 | view amenities | Done
83 | all amenities | Done
84 | add agency | Done
85 | update agency | Done
86 | delete agency | Done
87 | view agency | Done
88 | all agency | Done
89 | add agent | Done
90 | update agent | Done
91 | delete agent | Done
92 | view agent | Done
93 | all agent | Done
94 | add specialities | Done
95 | update specialities | Done
96 | delete specialities | Done
97 | view specialities | Done
98 | all specialities | Done
99 | add terms&conditions | Done
100 | update terms&conditions | Done
101 | delete terms&conditions | Done
102 | view terms&conditions | Done
103 | all terms&conditions | Done
104 | List of Conversations | Done
105 | Conversation Details (List of Messages) | Done
106 | Send/Receive Messages | Done
107 | Message Notification
108 | Message Counter | Done
109 | add admin Property | Done
110 | delete admin Property | Done
111 | update admin Property | Done
112 | view admin Property | Done
113 | all admin Property | Done